## Deliverables
Deliverables for Project
Deliverables
Work Package No | Deliverable Related No | Deliverable No | Deliverable Name | Description | Lead Beneficiary | Type | Dissemination Level | Due Date | New Due Date (if delay) | Delivery Date | Approval Date | Status
WP1 | D1.1 | D1 | Data Management Plan (DMP) v1 | Initial DMP describing data management lifecycle for data to be collected, processed and/or generated during/by the project, including the data types, reuse of existing data, operations to be performed, procedures to access data and prevent unauthorized use, sharing policies. The work for developing the DMP is conducted in Task 1.2. | FhG | DMP | PU | 30 Jun 2025 |  | 30 Jun 2025 |  | Submitted
WP1 | D1.2 | D2 | Ethics & AI Use Report v1 | Report containing a plan describing the planned AI algorithms and tools used in the project, including results on the technical robustness and reproducibility, integrity and accuracy, safety, social robustness, and ethical concerns. Specific steps taken to mitigate these identified concerns are also described. The work for developing this report is conducted in Tasks 1.2 and 1.3. | DTU | R | PU | 30 Jun 2026 |  |  |  | Pending
WP1 | D1.3 | D3 | Data Management Plan (DMP) v3 | Final DMP describing data management lifecycle for data to be collected, processed and/or generated during/by the project, including the data types, reuse of existing data, operations to be performed, procedures to access data and prevent unauthorized use, sharing policies. The work for developing the DMP is conducted in Task 1.2. | FhG | DMP | PU | 31 Dec 2027 |  |  |  | Pending
WP1 | D1.4 | D4 | Ethics & AI Use Report v2 | Final report describing the AI algorithms and tools used in the project, including results on the technical robustness and reproducibility, integrity and accuracy, safety, social robustness, and ethical concerns. Specific steps taken to mitigate these identified concerns are also described. The work for developing this report is conducted in Task 1.2 and Task 1.3. | DTU | R | PU | 31 Dec 2027 |  |  |  | Pending
WP1 | D1.5 | D5 | Data Management Plan (DMP) v2 | Interim DMP describing data management lifecycle for data to be collected, processed and/or generated during/by the project, including the data types, reuse of existing data, operations to be performed, procedures to access data and prevent unauthorized use, sharing policies. The work for developing the DMP is conducted in Task 1.2. | FhG | DMP | PU | 30 Jun 2026 |  |  |  | Pending
WP2 | D2.1 | D6 | Use cases, KPIs and technical and societal requirements | Report describing the refined analysis and specification from the bi0SpaCE use cases, corresponding KPIs, and stakeholder requirements based on results from Task 2.1. The descriptions of the user scenarios will include technical requirements for the solutions and technologies developed in bi0SpaCE (based on Task 2.2) as well as societal requirements identified through desk research and results from stakeholder requirements mapping (based on Task 2.3). | FhG | R | PU | 30 Sep 2025 |  |  |  | Pending
WP2 | D2.2 | D7 | bi0SpaCE ontologies | Semantics-based information modelling layer with ontologies and knowledge graphs. Definition of semantics-based information modelling layer applicable to bio-based sectors. Description of results from T2.4 implemented in the form of an open-access ontology model. | SSF | R | PU | 31 Mar 2026 |  |  |  | Pending
WP2 | D2.3 | D8 | bi0SpaCE technical architecture and data collection framework | Specification of the bi0SpaCE technical and system architecture. Results from mapping of pilot requirements to the technical functionality of the bi0SpaCE platform. The above results are based on work conducted in Task 2.5. Description of relevant data sources based on historical data from pilot partners, including metadata for each type of data source and data communication protocols. The above results are based on work conducted in Task 2.6. | FhG | R | PU | 31 Mar 2026 |  |  |  | Pending
WP3 | D3.1 | D9 | Technical documentation on sensor implementation and data pipe-lines | Data requirements for generating life-cycle inventories, data aggregation process, data collection infrastructure, communication protocols, and the identified data gaps for the four bi0SpaCE pilots. Report on sensor implementation, including technical specifications for the sensors and preliminary validation of data collection pipelines. The above results are based on work conducted in Task 3.1. | NISSA | R | SEN | 31 Mar 2026 |  |  |  | Pending
WP3 | D3.2 | D10 | Guidelines for environmental foot-printing of bio-based products | Report on guidelines including the definition of the KPIs in line with the requirements under the PEF and standards for bio-based products, as well as including definition of social and circularity indicators. Results from mapping bi0SpaCE pilot targets to the planetary boundaries framework to facilitate target setting for the pilots. The above results are based on work conducted in Task 3.2. | CAR | R | PU | 31 Mar 2026 |  |  |  | Pending
WP3 | D3.3 | D11 | Data-driven LCA & CE modelling framework | Methodology for data-driven modelling simulation for sustainability and circularity improvement of bio-based processes and products. Description of simulation methods and tools, model calibration and validation. The above results are based on work conducted in Task 3.3. Optimization framework for maximizing the sustainability and circularity performance assessed through simulation-based models under statistical uncertainties. Description of identified uncertainty sources and used sampling and ML-based optimization algorithms. The above results are based on work conducted in Task 3.4. Results for this deliverable are in the form of simulation models, software code, and technical documentation for implementing the simulation driven LCA & CE modelling and optimization. | AU | OTHER | PU | 31 Dec 2026 |  |  |  | Pending
WP3 | D3.4 | D12 | Policy recommendations for environmental footprinting of bio-based products | Policy brief describing the existing status, learnings, best practices, and guidance for conducting environmental footprinting studies of bio-based products with the goal of including these results in DPPs. The policy brief will be based on results from Task 3.2. | DTU | R | PU | 30 Jun 2026 |  |  |  | Pending
WP4 | D4.1 | D13 | ML models technology for bio-based process flows | Lab scale prototype of ML models for tracing continuous process flows in bio-based manufacturing. Results describing the validation of ML models based on offline, historical, simulation and experimental data. The above results are based on work conducted in Task 4.1. Results for this deliverable are in the form of digital models, accompanying datasets and technical documentation for training and validating the ML models. | AU | OTHER | PU | 31 Dec 2026 |  |  |  | Pending
WP4 | D4.2 | D14 | Enhanced resilience through improved materials tracing and flow modeling | Material tracing methodologies and data requirements for flow tracing and increasing resilience of biomass sourcing based on material flow analysis and transportation optimization. The above results are based on work conducted in Task 4.2. | SSF | R | PU | 31 Dec 2026 |  |  |  | Pending
WP4 | D4.3 | D15 | Digital tagging of bio-based products | Definition of standard protocol for tagging bio-based products. Description of data points and commonalities for digital tagging system. Implementation of proof-of-concept system for digital tagging as a lab scale prototype and validated using offline data from pilots. The above results are based on work conducted in Task 4.3. Results for this deliverable are in the form of datasets, algorithms, software implementation, and corresponding technical documentation. | CAR | OTHER | PU | 31 Dec 2026 |  |  |  | Pending
WP4 | D4.4 | D16 | Tracking and tracing technology validation | Tests results from validation of proof of concepts technologies of tracking and tracing from previous tasks at laboratory scale, based on offline data from pilots. Results evaluating preliminary DT platform integration interoperability with AAS representation for bi0SpaCE tracking and tracing technologies. The above results are based on work conducted in Task 4.4. | CAR | R | PU | 31 Dec 2026 |  |  |  | Pending
WP5 | D5.1 | D17 | AAS-compliant digital twins for bio-processes and DPPs for bio-products | AAS sub-model templates for bio-based processes and the life cycle of bio-products and services for DTs and DPPs. Configuration of connections between assets, sensors, external/internal software in the bi0SpaCE pilots for developing DTs. The above results are based on work conducted in Task 5.1. Software service for the creation of AAS-compliant DPPs for bio-based products based on results from Task 5.2. Results for this deliverable are in the form of software-based models and accompanying technical documentation. | FhG | OTHER | PU | 31 Dec 2026 |  |  |  | Pending
WP5 | D5.2 | D18 | bi0SpaCE data space | The result will be the bi0SpaCE dataspace for the exchange of DPPs of bio-based products. The bi0SpaCE dataspace will extend/customize the standard set of technical building blocks of a dataspace with a set of services specialized for the DPPs of bio-based products. These services include: - T5.3: a service for onboarding DPPs in a dataspace and a DPP registry to make the DPPs findable; - T5.4: a traceability service for DPPs that enables the track and trace functionality for DPPs of bio-based products in a value chain, including the primary and secondary materials used/generated; - T5.5: a service for consumers of DPPs in the form of an APP for customers and in the form of a client API for software systems that will use DPPs. T5.5. will also include integration, testing and deployment functionalities. We will deliver: - a report documenting all the research and technical challenges we need to address. - a set of software modules for all services to be developed (see above); - a running dataspace in which all these services are provided, and which can be used by external partners to share their DPPs. | FhG | OTHER | PU | 30 Sep 2027 |  |  |  | Pending
WP6 | D6.1 | D19 | Methodology of validation | Methodology to validate a new software framework in relevant use cases. Description of methodology for validating KPIs defined in bi0SpaCE pilots as well as achievable energy reductions and CO2 footprint reductions. These results are based on work conducted in Task 6.1. | CAR | R | PU | 30 Jun 2027 |  |  |  | Pending
WP6 | D6.2 | D20 | Validation in relevant environment | Demonstration of the bi0SpaCE software framework across the four use cases. Results validating the application of the bi0SpaCE software framework across the four use cases. These results are based on work conducted in Task 6.2-6.5. | DTU | DEM | PU | 31 Oct 2027 |  |  |  | Pending
WP6 | D6.3 | D21 | Lessons learnt and final results | Results and lessons learnt for the future based on use cases. Results quantifying the level of achievement of the use case objectives and identified KPIs. Mapping the results from the use cases to socio-technical requirements and recommendations for deployment of the bi0SpaCE software framework. These results are based on work conducted in Task 6.6. | CAR | R | PU | 31 Dec 2027 |  |  |  | Pending
WP7 | D7.1 | D22 | Dissemination and communication strategy | Plan on communication and dissemination activities in the project and generation of project visual identity, website, social media, and newsletters. These results are based on work conducted in Task 7.1. | NISSA | R | PU | 30 Jun 2025 |  | 30 Jun 2025 |  | Submitted
WP7 | D7.2 | D23 | Dissemination and communication report | Report describing results from the communication, dissemination, clustering, and liaison activities. These results are based on work conducted in Task 7.1 and Task 7.2. | NISSA | DEC | PU | 31 Dec 2027 |  |  |  | Pending
WP7 | D7.3 | D24 | Exploitation plan | Plan for results exploitation, detailing the consortium strategy for market entry, replication, transferability, and sustainability. These results are based on work conducted in Task 7.3. | NISSA | R | SEN | 31 Dec 2027 |  |  |  | Pending
WP7 | D7.4 | D25 | Standardization Roadmap and CWA project plan | Results of the standards mapping emerging standardization needs (addressed to CEN/ISO Technical Bodies) and the project plan of a new CWA. These results are based on work conducted in Task 7.4. | UNI | R | PU | 31 Dec 2027 |  |  |  | Pending
WP7 | D7.5 | D26 | Policy recommendations for standardization of DPPs for bio-based products | Policy brief describing the existing status, learnings, best practices, and guidance for standardization of DPPs for bio-based products. The policy brief will be based on results from Task 7.4. | UNI | R | PU | 31 Dec 2027 |  |  |  | Pending
WP7 | D7.6 | D27 | Exploitation Plan Draft | Draft version of results exploitation plan, outlining the consortium’s initial strategy for market entry, replication, transferability, and sustainability. These results are based on work conducted in Task 7.3. | NISSA | R | SEN | 30 Jun 2025 |  | 30 Jun 2025 |  | Submitted