## Slide 1: Update & Overview of deliverables

## Slide 2: Tasks and sub-tasks
WP | Task(s) and method(s) | Lead(s) | Output(s) and Deliverables | Update (September 2025)
1 Systematic reviews | 1.1 Systematic reviews and evidence synthesis (with machine learning) | Minx (with some help from Sovacool etc.) | Around 5 reviews, (1) one only on SRM, quite comprehensively, similar to the trilogy; (2) one on policies and social acceptance for both SRM and GGR (if we can); (3) one on SDG implications, also on side effects, co-benefits and barriers (for both SRM and GGR if we can); (4) one on carbon efficacy and performance and cost (SRM and GGR if we can) include perhaps here regional issues and spatial variation; one (5) on “geoengineering beyond the state” e.g. actors, business models and supply chains; one (6) possibly on interactions between SRM and GGR, as a feeder into WP5 | In progress, CDR looks very good, some work on SRM on mapping Also folded into the State of CDR
2 Bottlenecks | 2.1 The potential role of GGRs and SRM as part of a portfolio of climate mitigation measures | Riahi | At least two possible intermediate papers (likely more), at least a few interim scenario products. The first is work on interactions at the systems level; enabling conditions and acceleration; bottlenecks; feasibility (techno-economic, sociotechnical and political) The second is on (1) Transformations of demand-side systems (2) Public perception and individual preferences (3) Supply-side push through innovation, technology development and learning (4) Integration into renewable systems and energy efficiency (5) Offsetting residual GHG emissions to achieve climate neutrality | Updated the modelling framework to include all CDR options, writing a paper to understand configurations which will interact with the rest of the system, also work on tipping points and learning.
 | 2.2 Development of qualitative narratives | Riahi | Look at the narratives underpinning scenarios, theory of change that can accommodate the soft factors not usually represented in these calculations. Explores how public perception and individual preferences could develop into the future as well as formal representation of the dynamics in the quantitative modelling, linking closely to the surveys and data collection in WP3. | Looked into governance and institutional capacity, how it interacts with DAC, paper that Matt Giddens led on governance mechanisms. Will has done work on residual emissions, and Elina’s work on portfolios.

## Slide 3: Tasks and sub-tasks
WP | Task(s) and method(s) | Lead(s) | Output(s) and Deliverables | Update (September 2025)
3 Social acceptance | 3.1 Surveys and focus groups to determine public attitudes | Sovacool and Minx | For the public survey, we anticipate at least 10,000 respondents involving members of the public from at least 10 European countries as well as 10 other countries, including China, Brazil, India, Russia, and South Africa as well as the United States. To complement and supplement the survey, public focus groups will be conducted throughout Europe (across at least 10 countries, ideally with a mix or urban and rural areas) as well as the same other 10 non-European countries selected for the survey. The questions posed to the focus groups will also be similar to those presented in the survey. | First phase completed, second phase commencing (2026)
 | 3.2 Analysis of (social) media and emotions | Minx, also Lamb work on Lexis Nexus and media narratives | Very good here as a third method to help reveal people’s thoughts about trust or gender etc. Will also include stance detection and emotion stuff, pull in additional stuff from Twitter and sentiment analysis already discussed in other parts of the proposal | Completed: State of CDR paper, Twitter paper, responsible communication paper

## Slide 4: Tasks and sub-tasks
WP | Task(s) and method(s) | Lead(s) | Output(s) and Deliverables | Update (September 2025)
4 Learning and innovation | 4.1 Case studies of previously successful analogues | Nemet | A paper pulling together cases relevant for CDR technologies Another paper relevant for SRM technologies (including possible typology), the higher in the atmosphere you go, the more global the impacts, i.e. cloud brightening local, SAI more regional to global Then a synthesis of some sort, using the techno-economic lens, we place each GGR within a taxonomy of low-carbon technology types (Nemet, 2019). For each type, we will conduct case studies of previously successful innovations that are analogous in terms of socio-technical indicators: technology, scale, markets, adoption, system integration, and policy relevance (Grübler and Wilson, 2014). For each case we will focus on understanding the underlying factors creating the innovation gap, which from previous work we expect will involve demonstrations, scale up, niches, demand pull, and public acceptability | Completed with multiple papers from SHARD
 | 4.2 Accelerated learning | Nemet | One potentially crucial accelerator involves managing political economy considerations, which is informed by the political systems perspective. This analysis will deliver crucial insights on pathways to accelerating learning and adoption of key technologies required for achieving the long-term goals of the Paris Agreement. Policy stimulates technological change, that reconfigures political economy, creates a sort of feedback loop. | Completed: patterns of past change and acceleration, and accelerated diffusion, HATCH dataset

## Slide 5: Tasks and sub-tasks
WP | Task(s) and method(s) | Lead(s) | Output(s) and Deliverables | Update (September 2025)
 | 4.3 Patents and technology readiness | Minx and Nemet | Patents analysis and assessing technology readiness in terms of patenting activity, scientific progress and ownership.; no comprehensive information exists on which private and public organizations are actively developing and patenting these technologies | Completed: linkages paper has patents in that led by Finn, but a dedicated patents paper could be forthcoming
 | 4.4 Reliability and risk profiles | Fuss and Creutzig | They have six years of PhD, some sort of portfolio modeling, especially portfolios of GGR and SRM as a means to hedge risk, primarily for GGR. Focus on a crucial metric for investors, the permanence of total net CO2 sequestration, since credit for CO2 abatement depends on highly reliable sequestration | Completed: portfolio papers done as well as Quirina’s paper
 | 4.5 Portfolios of policy instruments. | Nemet, Sarah Luck, connections to WP6 as well | Portfolios within the innovation and support process, if you’re trying to support different technologies, how do you ensure your technology policy is robust, also mechanisms of technology push, innovation, demand pull. Patterns of learning and innovation. | Completed

## Slide 6: Tasks and sub-tasks
WP | Task(s) and method(s) | Lead(s) | Output(s) and Deliverables | Update (September 2025)
5 Benefits and risks | 5.1 Synergies and tradeoffs with water use and supply, food production, energy access, distributional effects and vulnerable populations, alongside climate change impacts. | Riahi, also Sabine Fuss work on biological refugia impacts, Reuben’s work on side effects, IIIASA work on carbon debts | This WP will use both model-based scenario analysis and expert elicitations to analyze the risks and trade-offs of SRM and GGR options. The model-based analyses will use extended tools surrounding IIASA’s MESSAGEix-GLOBIOM. A core focus will be on (1) competition between using land for GGR and for food production (Fujimori et al., 2019), which causes higher food prices and leads to adverse distributional impacts (2) implications on health as a consequence of potential slower emission reductions in the first decades of the century (Li et al., 2019) and of SRM methods themselves (Eastham et al., 2018) (3) consequences on water demand (Parkinson et al., 2019) for the production of biomass and of energy due to the extended use of combustion-based technologies that require cooling (4) implications for biodiversity through large-scale biomass plantations (5) Technology choices that prevent the application and learning of low carbon energy technologies as society expects that the availability of SRM and GGR later in the century may require less short-term mitigation action; and (6) Feasibility considerations around the financial transfers towards regions that deploy most of the SRM and GGR technologies (Honegger and Reiner 2018). | Partially covered in State of CDR, plus Jan S’s biodiversity work, but next big thing IIASA is doing will be fuller portfolio analysis

## Slide 7: Tasks and sub-tasks
WP | Task(s) and method(s) | Lead(s) | Output(s) and Deliverables | Update (September 2025)
 | 5.2 Expert elicitation and interviews | Sovacool | In parallel to these modelling components, we will conduct a series of expert interviews to elicit the expected risks arising from GGR and SRM deployment, including more extreme (and hence difficult to model) dynamics, such as their geopolitical implications, use as weapons, and so forth. | Completed (various papers)
 | 5.3 Synthetic synergies and risks within pathways | Sovacool | SDG work above will get into tradeoffs with some options, but not explicitly with mitigation, adaptation, etc. Will also explore synergies and risks between GGR and SRM technologies and across pathways (between mitigation, adaptation, etc.) as well as the risks of “cocktails” of poorly mixed options | Completed (Risk-Risk tradeoffs paper)

## Slide 8: Tasks and sub-tasks
WP | Task(s) and method(s) | Lead(s) | Output(s) and Deliverables | Update (September 2025)
6 Policy and governance | 6.1 Policy architecture | Sovacool and Minx, but also links to Sarah Luck’s inventory of policy, and the State of CDR report has sections on policy | The first part will document the existing policy architecture (policies, laws, regulations, statutes, codes, standards) for GGR and SRM within Europe. It will look at three different levels of policy: local (sub-national), national, and regional (mostly the European Commission). It will conduct an exhaustive content analysis to categorize and map GGR and SRM policies for all countries located within geographic Europe, from Iceland and the United Kingdom in the West to Russia in the East. The literature definitely makes a distinction between policies and regulations (including standards and laws), governance (including treaties and geopolitical concerns), and private sector/subnational actors. All three themes matter, but we may want to approach them differently in this WP. | Already have some work on NDCs and net-zero targets, cross cutting policy review
 | 6.2 Policy narratives | Minx and Sovacool | To examine policy and governance implications we will conduct sentiment analysis of public documents (i.e. parliamentary archives), drawing from approaches such as Tingley and Wagner (2017). Computer-assisted methods can apply discourse analysis at the appropriate level of scale to explore these themes. Focus on cultural discourse and media narratives. May search European Parliament or United Nations policy discourse only, due to English language restrictions. | Some on policy narratives, discourses of delay PIK can do data provision, but Aarhus to consider
 | 6.3 Policy options and policy feasibility | Sovacool | Drawing from WP1-WP4, qualitative interviews will be conducted with policymakers to determine which options and scenarios have the greatest political feasibility. To examine the systems of political action behind deployment pathways, a final task will test the resonance of the findings from WPs1-4 with actual policymakers. It will undertake further qualitative expert interviews with policymakers from around the world to better determine which SRM and GGR pathways have the most political legitimacy and feasibility. | Already begun with UPTAKE/ELEVATE interviews, N=92

## Slide 9: Tasks and sub-tasks
WP | Task(s) and method(s) | Lead(s) | Output(s) and Deliverables | Update (September 2025)
7 Synthesis | 7.1 Technological learning, diffusion and adoption, or socio-technical transitions | All, including State of CDR Report | Here we integrate the assessment of both technology-push and demand-pull factors: technology status and readiness as well as portfolio strategies (WPs 1 & 4), the coordination of GGR with other technologies and mitigation options (WP2), and current policy contexts around GGR (WP6). The expected outcome is to establish, for each GGR technology, potential rates of diffusion in Europe and barriers thereof. | Ongoing
 | 7.2 Risk management and ethical deployment | All | We will draw together aspects of risk management addressed in various segments of the project. In particular, our synthetic research will integrate results on regional siting constraints (WP1), public knowledge on technology risks (WP3), expert knowledge on deployment and extreme risks (WP5), and possible risk hedging strategies using portfolios of technologies (WP6). Together these will bring a new level of detail to contemporary discussions on the ethical use of GGRs as a climate mitigation strategy (Lenzi et al. 2018). | Ongoing
 | 7.3 Political economy sand justice | All | We will address the political economy and justice aspects of upscaling GGR technologies – a topic that has received very little treatment to date. Which countries and regions will host these technologies (WP1)? What preferences do the public have for them (WP3)? Who owns and will benefit from the technology patents (WP4)? And how are risks differentiated across various social groups (prior cross-cutting topic)? Understanding these questions will be crucial for alleviating distributional concerns and directly addressing them in the design of policies | Ongoing

## Slide 10: Tasks and sub-tasks
WP | Task(s) and method(s) | Lead(s) | Output(s) and Deliverables | Update (September 2025)
8 Impact | 8.1 GENIE Knowledge Hub | Riahi with support from all | The GENIE Knowledge Hub will feature three main types of tools: (1) Scenario portals – Building upon the IIASA’s leading role in the community to provide scenario explorers such as the one hosted for the IPCC SR1.5 (Huppmann et al, 2018), a new GENIE scenario portal will be established. The portal will allow flexible and interactive access to scenario inputs and outputs, and provide novel data analyses and visualization capabilities. We expect the portal to be a resource for the effective and comprehensive assessment of the future GGR and SRM deployment scenarios (developed in WP2 and WP5); (2) Technology databases – The Knowledge Hub will include web-based databases providing information about the techno-economic characteristics (costs and potential), but perhaps more importantly also public perception of different GGR and SRM options (derived from WP1 and WP2); (3) Infographics and interactive maps – These tools will focus on the translation and communication of the research insights for non-scientific and non-expert users. | Ongoing
 | 8.2 Policy briefs | All | Try to do them (A) when asked for from someone important or (B) whenever there is a pressing policy need or event. We will aim for at least six, possibly more. | SAPEA Report can count as a super policy brief Matt Giddens paper can be first one, European survey paper can be second one, then we aim for 4-6 more